# News-Section Project Status

Last Updated: 2026-01-25

## Current State

Project Phase: Phase 1 - Tag Infrastructure (IN PROGRESS)

Overall Progress: Phase 1 partially complete (~40%)

Status: Tag taxonomy complete, database schema specification complete

Completed This Phase: - Tag taxonomy finalized (~299 tags across 7 dimensions) - All tag definitions documented as atom files in /OnlyiGaming/tags/ - Primary triage rules, confidence thresholds, geographic model documented - Company extraction rules established - Database schema specification created (sql/schema.sql) ready for developer handoff

Documentation: Complete and validated - Shared tag source of truth: /OnlyiGaming/tags/ (atom/molecule architecture) - 81 directory categories (DIR) dir-categories.md - 45 news topics (NEWS) news-topics.md - ~115 geographic tags (GEO) geo-registry.md - 10 product verticals (PROD) prod-verticals.md - 16 publication types (TYPE) type-formats.md - 4 commercial status tags (COMM) comm-status.md - 28 career categories (CAREER) career-categories.md - Rule documents in /OnlyiGaming/tags/rules/: - primary-triage.md How to choose primary tags - confidence-thresholds.md AI auto-tagging score thresholds - geographic-model.md Independent region/country model - company-extraction.md How to identify and classify company entities - cross-section-discovery.md How related content displays across sections

## Highest Priority

Continue Phase 1: Tag Infrastructure Developer Handoff

Tag definitions and database schema specification are complete. Next step is handoff to site developer.

Completed: 1. Database schema specification (sql/schema.sql) aligned with Content-Pipeline 2. Cross-section discovery architecture (/OnlyiGaming/tags/rules/cross-section-discovery.md)

Next Steps: 1. Hand off sql/schema.sql to site developer for implementation 2. Coordinate with developer on tag seeding from /OnlyiGaming/tags/ atom documents 3. Review developer’s tag management admin UI design 4. Review developer’s CMS tag assignment interface design

Scope Clarification: - We provide specifications and tag definitions the site developer implements them - Content-Pipeline code is maintained separately (for content generation) - Website database code is owned by the site developer

Cross-Project Coordination: - Content-Pipeline shares the same tag taxonomy - Both projects should use /OnlyiGaming/tags/ as the seed source - Schema aligns with Content-Pipeline’s platform_tags table for future unification

## Active Blockers

None - Clear path to implementation.

All prerequisites are met: - Tag taxonomy finalized (~299 tags in /OnlyiGaming/tags/) - Platform integration patterns defined - Implementation roadmap approved - Technical requirements understood - Shared tag folder established as single source of truth

## Recommended Next Actions

### 1. Design Tag Database Schema

Objective: Create database tables aligned with Content-Pipeline

Concrete Steps: - Coordinate with Content-Pipeline on shared platform_tags schema - Define article_tags junction table with composite primary key - Define company_tags junction table with is_primary flag - Create indexing strategy for performance - Document foreign key relationships and constraints

Completion Criteria: - Database schema aligned with Content-Pipeline’s platform_tags table - SQL migration scripts written - Schema reviewed and approved - Performance implications understood

Estimated Time: 2-3 days

### 2. Populate Tags Database from Shared Source

Objective: Seed database from /OnlyiGaming/tags/ atom documents

Concrete Steps: - Parse atom documents from /OnlyiGaming/tags/: - dir-categories.md (81 DIR tags) - news-topics.md (45 NEWS tags) - geo-registry.md (~115 GEO tags) - prod-verticals.md (10 PROD tags) - type-formats.md (16 TYPE tags) - comm-status.md (4 COMM tags) - career-categories.md (28 CAREER tags) - Write import script with validation - Execute import and verify all tags loaded

Completion Criteria: - All ~299 tags loaded from atom documents - Tag counts verified by dimension - No duplicate tag IDs - Descriptions match atom source files

Estimated Time: 1-2 days

### 3. Build Tag Management Admin UI

Objective: Create administrative interface for managing tags

Concrete Steps: - Design UI wireframes for tag management - Implement CRUD operations (Create, Read, Update, Delete) - Build category organization view - Add search and filter functionality - Create tag usage analytics view - Implement bulk operations (import/export)

Completion Criteria: - Admin can view all tags organized by category - Admin can create, edit, delete tags - Admin can see tag usage statistics - Admin can export tags to CSV

Estimated Time: 3-4 days

## Phase Status Overview

| Phase | Status | Timeline | Progress | Dependencies Met |
| --- | --- | --- | --- | --- |
| Phase 1: Tag Infrastructure | IN PROGRESS | Week 1-2 | ~40% | Yes |
| Phase 2: Content Migration | Not Started | Week 3-4 | 0% | No (needs Phase 1) |
| Phase 3: Directory Integration | Not Started | Week 5-6 | 0% | No (needs Phase 1) |
| Phase 4: Platform Sections | Not Started | Week 7-8 | 0% | No (needs Phase 1, 3) |
| Phase 5: Main Navigation | Not Started | Week 9-10 | 0% | No (needs Phase 1, 2) |
| Phase 6: Search & Discovery | Not Started | Week 11-12 | 0% | No (needs Phase 1, 5) |
| Phase 7: Launch | Not Started | Week 13 | 0% | No (needs all phases) |

## Key Metrics (Not Yet Applicable)

Target Metrics for 30 Days Post-Launch: - Articles properly tagged: 95%+ - Average tags per article: 4-6 - Search usage increase: +50% - User engagement increase: +25%

Target Metrics for 60 Days Post-Launch: - Cross-section navigation: 30%+ - Saved searches created: 500+ - Email alerts active: 1000+ - Tag page views: 10K+

Target Metrics for 90 Days Post-Launch: - Directory usage increase: +40% - Tag CTR average: 3-5% - Cross-section traffic: 25%+

## Technical Decisions Made

### Cross-Section Content Discovery (2026-01-25)

Decision: Layered widget strategy with pre-computed semantic similarity

| Page Type | Widget Logic |
| --- | --- |
| Homepage / Landing | Latest (generic) ORDER BY date DESC |
| Category pages | Latest in category filter by tag |
| Detail pages | Related (contextual) pre-computed similarity lookup |

Implementation: - On content publish background job generates AI embeddings - AI finds semantically similar content across ALL sections - Stores top N matches in related_content table (website database) - Page load does fast lookup (no real-time AI)

Reference: /OnlyiGaming/tags/rules/cross-section-discovery.md

### Database Architecture

- Many-to-many relationships: Articles and companies can have multiple tags; tags apply to multiple items

- Primary tag concept: Companies have one primary DIR category plus secondary tags

- Tag categories: 7 distinct types (DIR, NEWS, GEO, PROD, TYPE, COMM, CAREER)

### Performance Strategy

- Indexing: Composite indexes on tag_id + article_id for fast lookups

- Caching: 1-hour cache for tag combination results, 30-min for directory pages

- Query optimization: Plan for 335+ tags with complex combination queries

### Validation Rules

- Minimum tags: 3-4 tags per article required

- Maximum tags: 8-10 tags per article to prevent over-tagging

- Required types: At least 1 NEWS tag and 1 GEO tag mandatory

- Conflict detection: Warn about incompatible tag combinations

### Migration Strategy

- Batch processing: Migrate historical content in controlled batches

- Rollback capability: Maintain ability to revert failed migrations

- Quality assurance: 5% random sample audit after migration

- Manual review: Editorial team handles edge cases and complex articles

## Open Questions

### Technical

- Database platform: MySQL, PostgreSQL, or other? (Decision needed before schema design)

- CMS platform: What existing CMS are we integrating with, or building custom?

- Caching layer: Redis, Memcached, or application-level caching?

- Search engine: Elasticsearch, Algolia, or database full-text search?

### Business

- Historical content volume: How many existing articles need migration?

- Editorial team size: How many people will be using the tagging system?

- Launch timeline: Is 13-week timeline firm or flexible?

- Beta user group: Who should be invited to beta testing?

### Process

- Approval process: Who approves each phase before moving to next?

- QA process: What testing standards must be met?

- Training timeline: When should editorial team training begin?

## Resources & Documentation

### Architecture Documents

- /docs/igaming_platform_complete_architecture_v5_3.md - Complete platform specification (current)

- /docs/FINAL_corrections_summary_v5.2.md - Version 5.2 corrections reference

### Project Context Files

- CLAUDE.md - Detailed project context for Claude AI

- GEMINI.md - Detailed project context for Gemini AI

- AGENTS.md - Quick reference for AI agents

- ROADMAP.md - 7-phase implementation plan

### Reference Data

- /docs/igaming news sites.xlsx - Competitive analysis

## Next Session Planning

When resuming work on this project:

- First Action: Review this PROJECT_STATUS.md to understand current state

- Read Architecture: Review /docs/igaming_platform_complete_architecture_v5_3.md for technical details

- Check Roadmap: Confirm Phase 1 tasks in ROADMAP.md

- Answer Open Questions: Resolve technical platform decisions before starting

- Begin Phase 1: Start with database schema design

Estimated Time to Productive Work: 15-20 minutes of context review

## Success Indicators

Project will be successful when: - ~299 tags enable precision content targeting - Articles automatically appear in relevant sections based on tags - Users navigate seamlessly across 8 platform sections - Editorial team finds tagging intuitive and valuable - Search and discovery metrics exceed targets - Monetization opportunities through tag sponsorships realized

Early warning signs to watch for: - Tag assignment confusion by editorial team - Performance degradation with complex queries - Low tag usage or over-reliance on few tags - User confusion with new navigation - Migration errors or data inconsistency

## Project Health: GREEN

- Complete documentation

- Clear implementation path

- No blocking dependencies

- Resources available

- Timeline realistic

- Technical approach validated

Ready to proceed with Phase 1 implementation.

## Session Log

### 2026-01-25: Cross-Section Content Discovery Architecture

Accomplishments: - Designed and documented layered widget strategy for cross-section content discovery - Created /OnlyiGaming/tags/rules/cross-section-discovery.md as architecture decision document - Updated ROADMAP.md with implementation details for Phase 4.7 and Phase 6.5 - Added Technical Decisions section documenting the architecture choice

Problem Solved: Different sections have different taxonomies (Jobs tagged by function, News by topic). Simple tag matching cannot connect semantically related content across sections.

Solution Decided: - Landing pages use “Latest” widgets (simple date query) - Category pages use “Latest in category” (filter by tag) - Detail pages use “Related” widgets (pre-computed semantic similarity lookup) - Background job on publish generates AI embeddings and stores top N matches - Page load does fast lookup from related_content table (no real-time AI)

Key Insight: AI embeddings capture semantic meaning, not keywords. A Job titled “ML Engineer - Player Safety” will be found as related to a Podcast about “AI in Player Safety” even with completely different tags.

Blockers: None

### 2026-01-25: Database Schema Specification

Accomplishments: - Explored Content-Pipeline’s existing platform_tags schema for alignment - Created comprehensive database schema specification (sql/schema.sql) - Defined tables: tags, articles, article_tags, companies, company_tags, related_content - Included indexes, constraints, validation rules, and helper views - Clarified scope: we provide specifications, site developer implements

Schema Highlights: - tags table: Synchronized from /OnlyiGaming/tags/ atom documents (~298 tags) - article_tags: Junction table with confidence scoring and source tracking - company_tags: Junction table with is_primary flag for primary DIR category - related_content: Pre-computed semantic similarity (per cross-section-discovery.md)

Scope Clarification: - News-Section project provides specifications for the site developer - We do not maintain the website database code - Content-Pipeline is the only code we develop

Blockers: None Ready for developer handoff