# Strategic Plan — Plasmic on Tailwind + Strapi (Hybrid Loader + Codegen)

## 1) Executive summary

We will layer Plasmic onto the existing Tailwind‑based frontend backed by Strapi to accelerate visual iteration (pages, layouts, components) without touching feature code, auth, or the CMS schema. We will use a hybrid approach: - Loader for fast, runtime‑fetched pages/sections owned by Design/Marketing. - Codegen for components that “graduate” into the codebase and require versioning, tests, and CI.

Expected outcomes within 4–6 weeks: - Time‑to‑publish new landing pages reduced from days to hours. - 50–80% fewer engineering hours spent on surface‑level UI changes. - Controlled, reversible publishing with clear QA and rollback.

## 2) Background & problem statement

- Visual change requests (LPs, hero swaps, seasonal banners) currently require developer time and deployments.

- Design and content teams depend on engineering for small changes, delaying campaigns and experimentation.

- The site uses Tailwind (atomic styling) and Strapi (content), which are stable; we want to edit only presentation while keeping application logic and CMS content intact.

Goal: decouple presentation from feature code so non‑developers can ship safe, high‑quality page changes rapidly.

## 3) Objectives and non‑goals

Objectives - Enable designers/marketers to create and publish pages and sections without PRs. - Preserve Tailwind as the styling foundation and maintain current build pipeline. - Keep Strapi as the content source; bind data into designs where needed. - Establish guardrails: QA, accessibility, SEO, performance budgets.

Non‑goals - No changes to authentication, server logic, or Strapi schemas. - No rewrite of application features; this is a presentation‑layer enhancement.

## 4) Why Plasmic now (business rationale)

- Speed to market: Launch and iterate campaigns in hours, not sprints.

- Team autonomy: Designers/marketers own landing pages and variants.

- Developer leverage: Engineers focus on features; UI chores shrink.

- Experimentation: Safer, faster A/B tests and CRO work.

- Consistency with control: Codegen promotes stable patterns into the repo.

## 5) Success metrics (KPIs)

- Lead indicator: median time from brief → published page (target: ≤ 1 business day).

- Dev effort saved: engineering hours/month on surface‑level UI reduced by ≥ 50%.

- Throughput: new pages/variants per month (baseline ×2).

- Quality: ≤ 1% of Plasmic publishes require hotfix rollbacks.

- Web vitals: LCP ≤ 2.5s, CLS < 0.1 for Plasmic pages.

## 6) Scope & constraints

- In‑scope: landing pages, marketing sections, nav/footers, promos, editorial modules, style refreshes.

- Out‑of‑scope: core app flows, payment/account/auth features, server logic, CMS schema migrations.

- Constraints: maintain accessibility (WCAG AA), SEO parity or better, Tailwind remains primary styling.

## 7) Architecture overview

Current: React/Next.js (assumed), Tailwind CSS, Strapi headless CMS, CI/CD to staging & production.

Target: - Plasmic Loader mounts at selected routes/slots. Designs are fetched at runtime and rendered inside the app shell. - Tailwind safelist patterns to prevent purge/JIT from removing classes used in runtime‑fetched designs. - Code components registration exposes existing React/Tailwind components to Plasmic Studio for drag‑and‑drop reuse. - Codegen for stable, shared UI pieces that require versioning/tests; generated components committed to the repo. - Data binding: Strapi JSON fetched in code and passed as props/slots into Plasmic components. - Guardrails: preview environment, QA checklists, automated Lighthouse budget checks, feature flags for rollout.

## 8) Integration approaches

| Approach | Pros | Cons | Recommended use |
| --- | --- | --- | --- |
| Loader only | Fastest setup; instant publish by non‑devs; no rebuilds needed | Tailwind purge needs safelist; less code ownership | Early landing pages, rapid tests |
| Codegen only | Full code ownership; versioned; no runtime fetch | Requires sync/PRs; slower iteration | Design‑system components, core layout primitives |
| Hybrid | Best of both: speed + stability | Slightly more upfront setup | Our default approach |

## 9) Roles & workflow

Roles - Design/Marketing: Build and edit pages in Plasmic Studio; run Figma → Plasmic import; publish within guardrails. - Frontend Devs: Integrate Loader, register code components, maintain Tailwind config, implement Codegen for stable parts, wire Strapi data. - QA/SEO: Validate accessibility, SEO meta, structured data, web vitals; approve publishes. - PM/Growth: Prioritize variants, track KPIs, coordinate experiments.

Workflow (happy path) 1. Designer imports Figma frame into Plasmic, assembles the page. 2. Dev reviews data bindings/props for Strapi content (if any). 3. QA runs checks in staging preview (Lighthouse, a11y, SEO, cross‑device). 4. Designer publishes via Plasmic; change appears in production. 5. Dev later promotes recurring modules to Codegen for reuse & tests.

## 10) Risks & mitigations

- Performance regressions → Budgets in CI, images optimized, lazy‑loading, limit third‑party embeds.

- Tailwind purge removes needed classes → Configure safelist patterns; document dynamic class usage.

- Design drift / inconsistency → Register core code components; style tokens; design review gates.

- Vendor lock‑in → Keep critical shared UI in Codegen; encapsulate Loader mounts; maintain fallbacks.

- SEO regressions → Pre‑publish checklist; automated tests for titles/meta/schema; monitor Search Console.

- Access & security → Role‑based Plasmic access; publish permissions; audit logs; feature flags.

## 11) Implementation plan & timeline (indicative)

Phase 0 — Pre‑flight (Week 1) - Audit candidate pages/sections; pick 2 pilot pages. - Provision Plasmic project; create /plasmic-host route; set up environments & tokens. - Add Tailwind safelist for runtime classes; document.

Phase 1 — Foundation (Week 2) - Install Loader in app; mount a test Plasmic page in staging. - Register 3–5 existing code components (Button, Card, Grid, Hero shell, Footer). - Create preview pipeline and QA checklist (Lighthouse, a11y, SEO).

Phase 2 — First pages (Week 3) - Import Figma frames for two pilot pages; bind Strapi content where needed. - QA + stakeholder sign‑off; publish to production via Loader.

Phase 3 — Hybridization (Week 4) - Promote stable modules to Codegen; add Storybook stories & unit tests. - Document designer playbook; training session.

Phase 4 — Scale‑up (Weeks 5–6) - Expand to top 10 landing pages; introduce experiment framework (A/B guidelines). - Add monitoring dashboards (web vitals, publish logs, rollback runbook).

## 12) Detailed technical steps (checklist)

- Install & configure

  - Add @plasmicapp/loader-* package; create plasmic-init.ts.

  - Add /plasmic-host for Studio live preview.

  - Configure env vars (public API token, project ID) via CI secrets.

- Tailwind integration

  - Confirm global Tailwind CSS import.

  - Add safelist regex for dynamic classes used in Plasmic runtime designs.

- Mount points

  - Identify routes/slots (e.g., /lp/*, homepage hero, footer promo) to render <PlasmicComponent name="…" />.

- Register code components

  - Wrap existing React/Tailwind components with registerComponent() including prop controls.

- Strapi binding

  - Fetch Strapi data in the page (REST/GraphQL); pass as props to Plasmic components; document typings.

- Codegen for stable modules

  - plasmic sync in CI; commit generated files; add tests; export via the design system.

- Quality gates

  - Automated Lighthouse budgets in CI; a11y (axe) checks; SEO meta/schema validation.

- Release & rollback

  - Publish permissions; staged rollout; instant revert via previous publish or feature flag fallback.

## 13) Governance & guardrails

- Publishing policy: Designers can publish to staging anytime; production publish requires QA checklist pass.

- Design tokens: Centralize color/spacing/typography; expose in Plasmic and Tailwind.

- Component graduation: Criteria for promoting Loader‑only sections to Codegen (used ≥3 times, stable for ≥2 weeks).

- Documentation: Repo README for setup; Designer playbook; QA checklist; rollback runbook.

## 14) Training & enablement

- Designers/Marketers: 90‑minute Plasmic Studio session + Figma import best practices; library of templates.

- Developers: 60‑minute session on Loader mounts, component registration, Codegen, and Strapi bindings.

- QA/SEO: 45‑minute session on checklists, automated reports, and web‑vitals dashboards.

## 15) Budget & resourcing (indicative)

- One‑time setup: ~0.5–1 dev‑day for integration; ~2–4 designer hours to import/finish first page.

- Ongoing: Designers publish independently; Devs maintain Codegen and component library during normal sprints.

- Licensing/infra: Plasmic plan (as required), no new core infra.

- ROI: Reclaim 50–80% of dev time previously spent on surface UI work; increase marketing throughput and experiment velocity.

## 16) Appendices

A. Pre‑publish QA checklist - Titles/meta/OG tags, canonical; schema where applicable. - LCP/CLS budgets met; images optimized; no blocking fonts. - a11y pass: landmarks, alt text, focus order, contrast. - Mobile/desktop cross‑browser visual QA.

B. Rollback runbook - Immediate revert to previous Plasmic publish; if needed, toggle feature flag to fallback server‑rendered section.

C. Naming & boundaries guidelines - Prefer semantic components (e.g., ProductCard, ArticleTeaser). - Keep components small; elevate repeating patterns to Codegen. - Document expected props and data shapes for each component.