## Tech - tasks
Task area | Main task | Subtask | Dependency | description | Figma link | Team | Task number
COMPANIES | Optimize speed |  |  |  |  | dev
Company Profile page
|  | F&Q on company profile | Community integration(chat integration) |  |  | Concept. UX, dev
|  | Additional functionlities |  | add book a demo. Add watch a demo. Book a customer review.
|  | Community/chat on each company profile | Community integration(chat integration) |  |  | Concept, UX, dev
|  | Better news, review, jobs visualization on profile page. |  |  |  | UX, dev
|  | Change the primary, secondary tags visualization |  | Hide full reviews, keep headline and stars. |  | UX, dev
|  | Imrpove sticky top . |  |  |  | UX, dev
|  | Right hand list. More then similar companies. |  |  |  | UX, dev
|  | Booking functionality with companies | Payment/booking development |  |  | Strategy, concept, UX, Dev
|  | Add demo video funtionality |  |  |  | Strategy, concept, UX, Dev
| ADd sections like /betsson/people betsson/insights. betsson/media |  | Content creation tool | new separate pages with content. |  | UX, Dev
| Company index optimization |  | Content creation tool | add more info, sections. news, reviews, comparisons, polls. |  | Strategy, concept, UX, dev
Implement changes in Strapi so that, as soon as a new company or news category is registered, a new meta description is automatically generated using the agreed structure and process. This task is dependent on the completion of the meta description strategy and template task.
REVIEW
| Add top banner and search + lists. |  |  |  | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=1-1794&t=hXl8JuluV07CxL7Z-1 | UX
| More review categories (for users to give stars to) |  |  |  |  | UX
|  | Categories: Price, service, features, implementation |  | Things like price, customer service, implementation, features, benchmark against others. Also specify if the person was a heavy user, if they did implementation, and when they used it. |  | Strategy, concept, UX; Dev
| . | Reviewer answers questions. HEavy user, buyer, when used, implemented.
| Create quick reviews |  |  | Where one can choose several companies and review them one at a time. Simplified review overview. |  | Strategy, Concept, UX, Dev
| Create bulk reviews |  |  |  | https://www.figma.com/design/Hdrn8rtw0w1izW5h3h4Qa3/only-igaming-development-wireframe?node-id=334-309&t=eePd83fG0Vfy2J33-1 | Strategy, Concept, UX, Dev
| Discussion possibility on review |  | Community integration(chat integration) | JUst like on google reviews. A discussion can and should be possible. |  | Strategy, Concept, UX, Dev
| Add contact/book meeting |  | Payment/booking development | The reviewer shall have the possibility to open up for a paid or unpaid chat regarding the usage, regardless of anonymity or using their name. set price per hour. |  | Strategy, Concept, UX, Dev
| add employer review option. |  |  | Let employees leave reviews on employer. | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11929-94083#1464197680 | Strategy, Concept, UX, Dev
1ST PAGE
| Bigger re-do |  | 4 column design, | Version 2 of converting the first page. After taking the low-hanging fruits with search and funnels, we might want to do more with sales. |  | Strategy, Concept, UX, Dev
REGISTRATION
| Registration. QUICK registration. first company info THEN account |  |  | Create funnel. Where the validation is after creation of company. |  | dev
| Tags feature - add new tag |  |  | Include the whole list of all licenses. Divided by countries. and then exact licenses. | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11898-18987#1461057810 | UX, Dev
| AI content creation for company profile. | Use our own content creation rpocess- | Content creation tool | Quicker registration process using our content tool. Also include upload of documents for source.
|  | Upload specific links or documnets. | Content creation tool
Add extra content questions to different categories.
|  | Affiliates - traffic source |  |  |  | Strategy, Concept, UX, Dev
|  | Payments providers. List of providers. |  |  |  | Strategy, Concept, UX, Dev
|  | Platforms sports (provider) |  |  |  | Strategy, Concept, UX, Dev
|  | Platforms casino (provider) |  |  |  | Strategy, Concept, UX, Dev
|  | Platforms payments (provider) |  |  |  | Strategy, Concept, UX, Dev
|  | Platforms gamification (provider) |  |  |  | Strategy, Concept, UX, Dev
|  | Platforms trackikng (provider) |  |  |  | Strategy, Concept, UX, Dev
| Use linkedin profile for company registration |  |  | When registering a company profile using linkedin, importing data directly, Needing better API We might need better API from LInkedin. |  | Dev
OMINPRESENT FEATURES
| 4 column design |  |  | The base for all future development should be a 4 grid system. This so we more easily can combine. | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=0-1&t=WwKFexf0ASerx0sc-1 | Strategy, Concept, UX, Dev
| User profile (big versatility) | Job Applilcant profile |  |  | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=55-4997&t=WwKFexf0ASerx0sc-1
|  | Networking profile |  |  | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=55-4997&t=WwKFexf0ASerx0sc-1
|  | Consultant |  |  | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=55-4997&t=WwKFexf0ASerx0sc-1
Bio (scraped content for articles/pods partiipants)
|  | Limited (hid)den |  |  | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=55-4997&t=WwKFexf0ASerx0sc-1
| My profile/dashboard |  |  | The personal profile with saved articles, jobs, companies, pods. History of meetings, demos etc.
Chat/discussion feature.
| Design tool - plasmic | Re-built front end
Connect backend
| Consultancy tool | Video meeting/stream through our site.
Meeting booking system
Connecting payments to booking.
Booking of video meeting
| Sourcing tools | Create favorites. |  | Save content pages (news, companies, jobs etc).
|  | Create shortlist - Comparisons |  | Create comparisons. Short summary, data and contact data.
|  | History - saving |  | Save who was sent a contact to, when. Later what calls where made.
| Tokens. | Expert tokens |  | Gamification. gamification points given for comments, polls, uploads, reviews, upvote/downvotes
|  | Consultancy tokens, |  | For small companies. There could be an exchange of services. Payment for a service is money or it could be banked and given in tokens, that can be redeemed later.
Banners on all pages.
|  | Banner system for planning ond organizing. |  | We need an internal system. where data can be shown to customers as well. Inhouse/outsource?
We need to design and create spaces for banners on all pages, desktop and mobile.
| Dashboard. Partners. |  |  | Just like aff papa. Have a dashbaord where stats for the different assets can be seen. Banners, company profiles, contacts etc.
CAREER PAGE
| Employee profiles |  |  | Core Concept Professionals can create iGaming-focused profile pages, importing data from LinkedIn or completing manually. Tagging by roles, tools, expertise, languages Visibility of availability (employed, freelance, seeking opportunities) Optional fee listings, ratings, Calendly integrations Cross-linked with job board, consulting and company listings Why It Matters Provides a structured search alternative to LinkedIn Enables talent visibility for active and passive candidates Supports scouting, networking, and hiring directly from the platform
| Increase options for employee branding. |  |  | Allow companies to build a dedicated career-focused presence — separate from their product/service listings — to showcase their team culture, values, and open roles.
| Dedicated project recruitment. |  |  | Short-term consulting/project work posted by companies in need of specialized, time-limited help. Tightly integrated with the existing OnlyiGaming Marketplace.. Combine the present Job offer possibilities with the consultant page. Include. Preoject pitch. Stake options, time estimate, finders fee if include more consultants.
|  | implement options for 3rd party contracts, hire and payroll. Easy management of projetc |  | Make deals with existing 3rd party products.
| Create a tip functionality. Where a tip for a job gives a reward if hired. |  |  | Create a bigger viral effect.
| Integration with gambling careers, |  |  | To be able to get some income we integrate and offer packages. But then also backend/dashboard
| Career planning page |  |  | Tips, articles, videos, checklists etc. Salary lists.
CONSULTING PAGE
| TRaditional marketplace - consultants |  |  | Copy what is on companies. But with consultants. But with more categories and more detailed categories.
| Expert consultants |  |  | NExt level is to create much deeper expertise categories. Options to uplaod white papers, cases, connect to companies.
| Micro consultations | The actual session is outside the site. |  | The possibility to book single sessions from 30min-2 hours. Payment insite. Session in 3rd party tool
|  | Session inside the site. | Streaming tool. | Tool inside the site
| Create consultants Profile page |  |  | Create a similar thing for companies with news, case uploads, blogs, tips, tricks, videos, and reviews. We need a category system, tags, price, and book a call.
NEWS PAGE
| MVP1 | First page. Simple article listigs on 2nd level. | Plasmic integration | https://docs.google.com/document/d/102RYEAap5LNg51dPvGSBSOBaG17ywqI6_H2Ke8SwmJo/edit?tab=t.0 | https://www.figma.com/design/WjTJVHADecREjiybyo1g1P/New-development-nov?node-id=16-1124&t=FrwkuWTabC59BaZ2-1
| MVP2 | • Main news sections (Deals & Money, People & Moves, etc) | Plasmic integration
|  | • Site sections (Marketplace, Careers) | Plasmic integration
|  | • Directory categories (Casino Platform, Payment Gateway) | Plasmic integration
MARKETPLACE - M&A page
| Investment listing |  |  | Just like the company profile pages: just a little different info on the pages. Search and results page. Very similar to the company profile page.
| Investor profiles |  |  | Create profiles for the investors. With wishe, interests. This to be able to combine the actual cases that come in actively.
Create / Start-up | The hub for creativity. |  |  | Create a page where people can have discussions. Create project pages. Invite or advertise for people to
|  | Project page. |  | LIke a company page. Description. some details.
|  | Project members. |  | Profile creation.Very similar to
|  | Prototype poll |  | Creating solution where a draft, sketch, document can be commented, tested or polled.
|  | Forum |  | Open forum
|  | search experts |  | Open search for people who want to iteract in this arena see co-founderslab
Community | Community page MVP
|  | Community landing page | Registrations required. (private) | Create something like a mix of reddit and linkedin. Threads, themes etc. Polls. | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11905-22265#1461611440
|  | Polls |  | Poll functionality should be included.
Connect telegram channels to the community.
|  | Different groups (according to directory categories, |  | Simple functionality of comments to companies, news, pods etc
Commenting functionality - reviews
Commenting functionality - articles
Commenting functionality - FAQ
Commenting functionality - Companies
SEO / content |  |  |  | https://docs.google.com/document/d/1_kFflCcglopH8_Xj-0pBU4MQ_4dexZFR5k9z7LLD6R8/edit?usp=sharing
| Implement schema from Stefan file on companies and categories. |  |  | https://docs.google.com/document/d/1UnvASvwSZ29jGg-NWjbDvFhzvUvxJKUpdTTVbME2R10/edit?usp=sharing
FAQ on top 5 categpries.
Create top keywords for each categoruy
Create comparisons
OPTIMIZATION/CMS/SEO
Create the schema list.
SEO Assessment of Updated Category List
| Update Next auth to v5. |  |  | 8 hours
| Update Strapi CMS to v5 |  |  | 16 hours
| Update Tailwind to v4. |  |  | 8 hours
| Update Next.js to v15 |  |  | 20 hours
UPdate robots.txt
| Create text and SEO possibility for each and every category. |  |  | Have Stefan create texts for each and every category, as well as the top category.
| prompt structure- meta description. |  |  | Define and implement a structured approach for meta descriptions on company profile pages. The goal is to differentiate OnlyiGaming’s listings from official company sites by highlighting unique value, such as comparisons, unbiased reviews, and interactive resources. Decide on the process for generating these descriptions (manual, AI-generated with QA, or a specific template). Prepare a list of company-specific descriptions for AI generation. This will improve search visibility and click-through rates.
AWARDS PAGE | AWARDS PAGE
| Create a page with different yearly and monthly awards and stats. |  |  | It would need more visitors and activity.
COMMUNICATION CHANNELS |  |  |  | This is where different omnipresent communication channels shall be planned and developped. These tools and channels cna be used by every section of the site.
Create Telegram Channel
Create Signal Channel
Create WhatsApp Channel
Create Discord Channel
| Create Newsletters |  |  | We need to utilize the data we have.
Create an Internal Substack
Create Automatic Publishing on the Channels from the Scraped News Section
Sales funnel - e-mail
CO-OPERATIONS
Research and data companies
| M&A person |  |  | In order to fill up the database with consultants, both for 1-hour video stream chats and longer consultancies we need to do an outreach in linkedin.
Community person
Consultancy person
Podcast/streamer person
CALENDAR/EVENTS PAGE |  |  |  | Create different calnedars. LIke Offlince events, conferencese. Scrub for info. online events. Webinars - podcasts live. Demo. company/Software specific. Needs applying.
Create a concept for events.
STREAMING
Research and conceptualize streaming.
CONTENT CREATION
Automatic content creation platform
Create company profile
Create news section
Create meta tags meta descriptions
Create FAQ for all categories
Create reviews. Comparisons
Create Podcast content.
Create content plan for YouTube group
Create content plan for Signal group
Create content plan for Discord group
Create content plan for Telegram group
Create content plan for WhatsApp group
Create content plan for company section
Create content plan for LinkedIn v2
Create content plan for News section
EDUCATION PAGE
| Create concept for education section. |  |  | Co-oå with igaming academy etc. Youtube shorts with 20-30 sec educational content.
Backlogg improvements
| Add tags in filter. |  |  |  | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11830-10204#1461381672
| News section. adjust design - typography |  |  |  | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11901-22204#1461378064
Tags feature - specify engagement model
| Update company licenses field |  |  | Create new license collection type on the backend Import list of licences from Add a search filter, like keyword search. results come up in the list. user clicks and then clicks “add” | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11896-13521#1461059501
Improved register funnel
Split result page between primary and secondary categories
⁠Improved formating of headlines and text in banners
| Adapted company profile visualization depending on search term (in old figma file) |  |  |  | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11847-10212#1464371646
| Improve category and Tags visualization in company profile |  |  |  | https://www.figma.com/design/1Zp68qVGHi00ZJU4HNPd0t?node-id=11847-10214#1464370934
| Load all content pages in quick view. |  |  | To be able to browse a large list and not having to load new pages all the time. Loading a company in loayover and not loose position on page.

## non development tasks
Task area | Task Name | Subtask | Dependency | description | Figma link | Team | Task number
Concept (strategy) | Consulting pages |  |  |  |  | Daniel | CS 1
|  | Profile consultant |  |  |  | Daniel | CS 1.1
| community page |  |  |  |  | Daniel | CS 2
| M&A pages |  |  |  |  | Daniel | CS 3
| pods/media page |  |  |  |  | Daniel | CS 4
| News page. |  |  |  |  | Daniel | CS 5
| Profile variations |  |  |  |  | Daniel | CS 6
Optimization (Mihail/daniel) | distiction: primary/secondary category |  |  | We should take out a list of all companies. And rank them with most categories. Go through 1by 1 and select promary and secondary categories.
| Category description. |  |  | We should go through category by category. Optimize the decription. Because this is the base for the FAQ creation.Its is also the base for the AI to determine and suggest company category and subcategories. https://docs.google.com/spreadsheets/d/1u73XQl5PFHaUKos0ysXU79HsuyJ7aNnNLdXU-V1FWhY/edit?usp=sharing
Design (joseph) | Banners |  |  | Joseph should check the brand ambassador and design |  | Design - Joseph
| colors |  |  | We need to include more colors. |  | Design - Joseph
UX - Development
| NEws section |  | CS 5
|  | subsection - main news sections (ie: deals & money) | CS 5
|  | subsection site section (ie: marketplace, careers) | CS 5
|  | subsection - directory category. (casino platform, payment gateway) | CS 5
| Community | Landing page | CS 2
|  | Underneath articles, podcast, posts | CS 2
|  | specific discussion page | CS 2
| Profile template | Personal profile | CS 6
|  | networking profile (linkedin) | CS 6
|  | Job searcher(talent) | CS 6
|  | Consultant profile | CS 6
|  | Bio profile (people mentioned in articles, podcasts, posts) | CS 6
|  | Investor profile | CS 6
| Content pages template | CDirectory company
Employer
POdcastg
NEws article
Investment project/company
Project - Start-up colaboration
Project brief (companies looking for freelancers to do a project)

## Done
1003. Footer | Footer change | 4 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-4304&t=wypFYutGQP9eol91-1
1004. Top menue desktop- format issue | Top menue. - desktop. alignment | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=0-1&t=wypFYutGQP9eol91-1
1008. Top banner companies Mobile | company page - change top banners | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-9295&t=wypFYutGQP9eol91-1
1009. Top banner Companies search. | Company page - search mechanics |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-9981&t=wypFYutGQP9eol91-1
1002. Result page. CTA + padding change | Change the CTA banner - desktop | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-2495&t=wypFYutGQP9eol91-1
1002. Result page. CTA + padding change | Adjust padding in banner for job search | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-2495&t=wypFYutGQP9eol91-1
1001. Format job profile | Job add description page. Formatting improvements | 5 | https://www.figma.com/design/https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=0-1&t=wypFYutGQP9eol91-1?node-id=11811-44091#1460347278
1010. Company profile. Show all. | company description page. Improve formating. (m + d) | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=24-5816&t=wypFYutGQP9eol91-1
1011. Add amount of jobs in search results | Add amount of jobs in each filter | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=24-33972&t=wypFYutGQP9eol91-1
1007. Improve Search on career page. | The search is not consistent on mobile. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-8718&t=wypFYutGQP9eol91-1
1005. Top menue - mobile | Meta navigation (m) | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-6775&t=wypFYutGQP9eol91-1
1012. Sign up. 3 funnels | 3 conversion funnels. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-3774&t=cD2L4Amd2n8NXbTo-1
1013. ALL Search bars. Dark background |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-18746&t=cD2L4Amd2n8NXbTo-1
1016. Hamburger menue - consistent usage. | Hamburger menue (m) - Just do it | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-36968&t=cD2L4Amd2n8NXbTo-1
1017. Layover consistency. | Apply layover - concistent | 1 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-39352&t=cD2L4Amd2n8NXbTo-1
1015. Career index page banners (mobile). | Remove the complicated search boxes. Add only keywords search. That is merely a link to open the whole serach layover. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-30563&t=cD2L4Amd2n8NXbTo-1
1018. Fix search layover on mobile. | Layover pages do not seem to have the same formatting. Please make it the same across the site. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=56-48748&t=cD2L4Amd2n8NXbTo-1
1019. Job description in registration | Several changes in the job add registration form. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=37-4246&t=cD2L4Amd2n8NXbTo-1
1020. Padding and distance - result page |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=39-4855&t=cD2L4Amd2n8NXbTo-1
1021. Banner link. Change |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6076&t=cD2L4Amd2n8NXbTo-1
1022. LInks from Feutured companies - not working. |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6112&t=cD2L4Amd2n8NXbTo-1
1023. Layover need to be a regular page, with URL |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6130&t=cD2L4Amd2n8NXbTo-1
1024. Link to relevant job search. | The suggestions on job description page shold be from the search and not from the actual company. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6821&t=cD2L4Amd2n8NXbTo-1
1027. similar companies visualization. | This functionality does not seem to work after orinary and secondary categories are live |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=56-36188&t=cD2L4Amd2n8NXbTo-1
1028. Filters on MObile? | I can not find the filters page att all. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=58-18286&t=cD2L4Amd2n8NXbTo-1
1029. Small typography and tags issue. Recommendation |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=93-16307&t=cD2L4Amd2n8NXbTo-1
1026. New banners and widgets . |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6844&t=cD2L4Amd2n8NXbTo-1
1025. Advertise with us page. Overlay. |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6843&t=cD2L4Amd2n8NXbTo-1
1014. Tags placement (mobile) | On mobile the choosing tags is really confusing and bad. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-22326&t=cD2L4Amd2n8NXbTo-1

## Design changes 22
| description | Done | link
1004. Top menue desktop- format issue | Top menue. - desktop. alignment | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=0-1&t=wypFYutGQP9eol91-1
1008. Top banner companies Mobile | company page - change top banners | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-9295&t=wypFYutGQP9eol91-1
1009. Top banner Companies search. | Company page - search mechanics |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-9981&t=wypFYutGQP9eol91-1
1002. Result page. CTA + padding change | Change the CTA banner - desktop | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-2495&t=wypFYutGQP9eol91-1
1002. Result page. CTA + padding change | Adjust padding in banner for job search | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-2495&t=wypFYutGQP9eol91-1
1001. Format job profile | Job add description page. Formatting improvements | 5 | https://www.figma.com/design/https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=0-1&t=wypFYutGQP9eol91-1?node-id=11811-44091#1460347278
1010. Company profile. Show all. | company description page. Improve formating. (m + d) | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=24-5816&t=wypFYutGQP9eol91-1
1011. Add amount of jobs in search results | Add amount of jobs in each filter | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=24-33972&t=wypFYutGQP9eol91-1
1007. Improve Search on career page. | The search is not consistent on mobile. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-8718&t=wypFYutGQP9eol91-1
1005. Top menue - mobile | Meta navigation (m) | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-6775&t=wypFYutGQP9eol91-1
1012. Sign up. 3 funnels | 3 conversion funnels. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-3774&t=cD2L4Amd2n8NXbTo-1
1013. ALL Search bars. Dark background |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-18746&t=cD2L4Amd2n8NXbTo-1
1016. Hamburger menue - consistent usage. | Hamburger menue (m) - Just do it | 5 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-36968&t=cD2L4Amd2n8NXbTo-1
1017. Layover consistency. | Apply layover - concistent | 1 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-39352&t=cD2L4Amd2n8NXbTo-1
1015. Career index page banners (mobile). | Remove the complicated search boxes. Add only keywords search. That is merely a link to open the whole serach layover. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-30563&t=cD2L4Amd2n8NXbTo-1
1018. Fix search layover on mobile. | Layover pages do not seem to have the same formatting. Please make it the same across the site. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=56-48748&t=cD2L4Amd2n8NXbTo-1
1019. Job description in registration | Several changes in the job add registration form. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=37-4246&t=cD2L4Amd2n8NXbTo-1
1020. Padding and distance - result page |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=39-4855&t=cD2L4Amd2n8NXbTo-1
1021. Banner link. Change |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6076&t=cD2L4Amd2n8NXbTo-1
1022. LInks from Feutured companies - not working. |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6112&t=cD2L4Amd2n8NXbTo-1
1023. Layover need to be a regular page, with URL |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6130&t=cD2L4Amd2n8NXbTo-1
1024. Link to relevant job search. | The suggestions on job description page shold be from the search and not from the actual company. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6821&t=cD2L4Amd2n8NXbTo-1
1027. similar companies visualization. | This functionality does not seem to work after orinary and secondary categories are live |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=56-36188&t=cD2L4Amd2n8NXbTo-1
1028. Filters on MObile? | I can not find the filters page att all. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=58-18286&t=cD2L4Amd2n8NXbTo-1
1029. Small typography and tags issue. Recommendation |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=93-16307&t=cD2L4Amd2n8NXbTo-1
1026. New banners and widgets . |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6844&t=cD2L4Amd2n8NXbTo-1
1025. Advertise with us page. Overlay. |  |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=41-6843&t=cD2L4Amd2n8NXbTo-1
1014. Tags placement (mobile) | On mobile the choosing tags is really confusing and bad. |  | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=32-22326&t=cD2L4Amd2n8NXbTo-1
1003. Footer | Footer change | 4 | https://www.figma.com/design/MWFuDjsoLCLMofBduvNFDZ/Design-changes-10.25?node-id=1-4304&t=wypFYutGQP9eol91-1